## Team Members
Team Member | Contact Phone | Normal Hours | Normal Workdays
Bob Smith | 555-5676 | 8 | Mon - Fri
Sue Jones | 555-2567 | 8 | Mon - Fri
Tim Thomas | 555-2243 | 8 | Mon - Fri

## Roles
Role | Team Member
Project Manager | Randal Root
Documentation Developer | You
Data Warehouse Developer | You
ETL developer | You
Cube Developer | You
Report Developer | You
Testers | You
Release Manager | You

## Solution Schedule
BI Solution Projects | Est Hours | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10
Interview and Identify: | 28 | Wk1: ***************************
Planning and Documenting: | 18 | Wk3: ****************
Create the Data Warehouse | 3 | Wk5: *********; Wk6: ****
Extract, Transform, and Load: | 6 | Wk6: *****************
Create Cubes: | 6 | Wk8: *********
Create Reports: | 6 | Wk9: *********
Test the Solution: | 21 | Wk10: ********
Approve, Release, and Prepare for next version: | 9 | Wk10: ********

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner | 3
|  | Talk to Mangers | 3
|  | Talk to Users | 3
|  | Talk to DBA | 3
| Document Requirements | Create an informal overview | 3
|  | Create a BI solution worksheet | 3
| Locate Data | Review database tables | 3
|  | Review invoice documents | 3
|  | Review sales awards program | 3
| Discuss Feasibility | Decide if the solution will work | 1
28
Planning and Documenting: | Define Team Roles | What role fit this solution? | 1
| Define Team Members | Who will fill each role? | 1
| Define Team Schedule | When will we need them? | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS | 1
|  | Verify a time slot of Solution automation jobs | 1
| Define Security requirements | Decide which groups will have access to what? | 1
| Define Licensing requirements | Verify that the company has sufficient licensing | 3
| Estimate the cost | Hours * Wages + and additional 10% for unknowns | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Create formal documents | Complete BI solution worksheet | 3
|  | Create a Development Document | 3
18
Create the Data Warehouse | Create the Database | Create the Tables | 2
|  | Define Constraints | 1
3
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code | 3
|  | Create a an SSIS package with ETL code | 3
6
Create Cubes: | Create SSAS Database | Create Dimensions | 3
|  | Create Cubes | 3
6
Create Reports: | Create Prototype Reports | Create SSRS Reports | 3
|  | Create Excel Reports | 3
6
Test the Solution: | Requirements | Verify naming | 3
|  | Verify data domains | 3
|  | Verify formula results | 3
|  | Verify presentation formatting | 3
| Performance | Test SSIS ETL performance | 3
|  | Test SSAS Processing performance | 3
|  | Test SSRS Report performance | 3
21
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document | 3
|  | Create a formal overview document | 3
|  | Create a lessons learned document | 3
9
|  | TOTAL | 106.7

## Data Warehouse
Data Warehouse Objects Worksheet
Object Name | Description | Source | Source Type | Destination Type | Transformations | KEEP or Don't? | Why or Why Not?
DWAdventureWorks_Level01 | Data Warehour Database | AdventureWorks_Level01 | Database | Database
DWAdventureWorks_Level01.dbo.DimProducts | Dimension Table Data | AdventureWorks_Level01.dbo.Products | Table | Table |  | Keep | Must have it to show product sales
DWAdventureWorks_Level01.dbo.DimProducts.ProductKey | Dimension Surrogate Key | NA | NA | int |  | Added | Added for Future SCD Support
DWAdventureWorks_Level01.dbo.DimProducts.ProductID | Dimension Key Column | AdventureWorks_Level01.dbo.Products.ProductsID | int | int |  | Keep | Must have it to link to other tables and is the Key Identifier
DWAdventureWorks_Level01.dbo.DimProducts.ProductName | Dimension Column | AdventureWorks_Level01.dbo.Products.Name | nvarchar | nvarchar (50) |  | Keep | Must have it to provide human-friendly name
DWAdventureWorks_Level01.dbo.DimProducts.StandardListPrice | Dimension Column | AdventureWorks_Level01.dbo.Products.ListPrice | money | decimal (18,4) | Cast to Decimal(18,4) | Keep | Nice to have it to show difference between actual sales price and suggested price
DWAdventureWorks_Level01.dbo.DimProducts.ProductSubcategoryID (Redundent) | Dimension Column (FK) | AdventureWorks_Level01.dbo.Products.ProductSubcategoryID | int | int |  | Keep | Nice to have it so that links can be made to source data easily
| Dimension Column | AdventureWorks_Level01.dbo.Products.SafetyStockLevel | smallint | NA |  | Don’t Keep | Not needed since this does not provide useful report data
| Dimension Column | AdventureWorks_Level01.dbo.Products.ProductLine | nchar | NA |  | Don’t Keep | Not needed since this data does not appear to be complete (Suspect)
DWAdventureWorks_Level01.dbo.DimProducts (Part of DimProducts, Star Design) | Dimension Table Data | AdventureWorks_Level01.dbo.ProductSubcategory | Table | Table |  | Keep | Must have it to show product sales by subcategory
DWAdventureWorks_Level01.dbo.DimProducts.ProductSubcategoryID | Dimension Key Column | AdventureWorks_Level01.dbo.ProductSubcategory.ProductSubcategoryID | int | int | Change Nulls to -1 | Keep | Must have it to link to other tables and is the Key Identifier
DWAdventureWorks_Level01.dbo.DimProducts.ProductSubCategoryName | Dimension Column | AdventureWorks_Level01.dbo.ProductSubcategory.Name | nvarchar | nvarchar (50) | Change Nulls 'NA' | Keep | Must have it to provide human-friendly name
DWAdventureWorks_Level01.dbo.DimProducts.ProductCategoryID (Redundent) | Dimension Column (FK) | AdventureWorks_Level01.dbo.ProductSubcategory.ProductCategoryID | int | int |  | Keep | Nice to have, so that links can be made to source data easily
DWAdventureWorks_Level01.dbo.DimProducts (Part of DimProducts, Star Design) | Dimension Table Data | AdventureWorks_Level01.dbo.ProductCategory | Table | Table |  | Keep | Must have it to show product sales by category
DWAdventureWorks_Level01.dbo.DimProducts.ProductCategoryID | Dimension Key Column | AdventureWorks_Level01.dbo.ProductCategory.ProductCategoryID | int | int | Change Nulls to -1 | Keep | Must have it to link to other tables and is the Key Identifier
DWAdventureWorks_Level01.dbo.DimProducts.ProductCategoryName | Dimension Column | AdventureWorks_Level01.dbo.ProductCategory.Name | nvarchar | nvarchar (50) | Change Nulls 'NA' | Keep | Need it to provide human-friendly name
DWAdventureWorks_Level01.dbo.Customer | Dimension Table Data | AdventureWorks_Level01.dbo.Customer | Table | Table |  | Keep | Must have it to show customer sales
DWAdventureWorks_Level01.dbo.DimCustomers.CustomerKey | Dimension Surrogate Key | NA | NA | int |  | Added | Added for Future SCD Support
DWAdventureWorks_Level01.dbo.DimCustomers.CustomerID | Dimension Key Column | AdventureWorks_Level01.dbo.Customer.CustomerID | int | int |  | Keep | Must have it to link to other tables and is the Key Identifier
DWAdventureWorks_Level01.dbo.DimCustomers.CustomerFullName | Dimension Column | AdventureWorks_Level01.dbo.Customer.FirstName | nvarchar | nvarchar (100) | Concatenate First and Last Names | Keep | Need it to provide human-friendly name
DWAdventureWorks_Level01.dbo.DimCustomers.CustomerFullName | Dimension Column | AdventureWorks_Level01.dbo.Customer.LastName | nvarchar | NA | Concatenate First and Last Names | Keep | Need it to provide human-friendly name
| Dimension Column (FK) | AdventureWorks_Level01.dbo.Customer.AddressID | int | NA |  | Don’t Keep | Not needed since this is too detailed for meaningful grouping of sales data
| Dimension Column | AdventureWorks_Level01.dbo.Customer.AddressLine1 | nvarchar | NA |  | Don’t Keep | Not needed since this is too detailed for meaningful grouping of sales data
DWAdventureWorks_Level01.dbo.DimCustomers.CustomerCityName | Dimension Column | AdventureWorks_Level01.dbo.Customer.City | nvarchar | nvarchar (50) |  | Keep | Must have to group customers sales by city
DWAdventureWorks_Level01.dbo.DimCustomers.CustomerStateProvinceName | Dimension Column | AdventureWorks_Level01.dbo.Customer.StateProvinceName | nvarchar | nvarchar (50) |  | Keep | Must have to group customers sales by state
DWAdventureWorks_Level01.dbo.DimCustomers.CustomerCountryRegionCode | Dimension Column | AdventureWorks_Level01.dbo.Customer.CountryRegionCode | nvarchar | nvarchar (50) |  | Keep | Nice to have to group customers sales by commonly used country codes
DWAdventureWorks_Level01.dbo.DimCustomers.CustomerCountryRegionName | Dimension Column | AdventureWorks_Level01.dbo.Customer.CountryRegionName | nvarchar | nvarchar (50) |  | Keep | Need it to provide human-friendly name
| Dimension Column | AdventureWorks_Level01.dbo.Customer.PostalCode | nvarchar | NA |  | Don’t Keep | Not needed since this is too detailed for grouping and has a Many to Many relationship to City!
| Dimension Column (FK) | AdventureWorks_Level01.dbo.Customer.BusinessEntityID | int | NA |  | Don’t Keep | Not needed since we can link to source data with CustomerID
DWAdventureWorks_Level01.dbo.FactSalesOrders (Part of fact table) | Dimension Table Data | AdventureWorks_Level01.dbo.SalesOrderHeader | Table | Table |  | Keep | Need it to provide individual Sales orders
DWAdventureWorks_Level01.dbo.FactSalesOrders.SalesOrderID | Dimension Key Column | AdventureWorks_Level01.dbo.SalesOrderHeader.SalesOrderID | int | int |  | Keep | Must have it to link to other tables and is the Key Identifier
DWAdventureWorks_Level01.dbo.FactSalesOrders.OrderDateKey (FK) | Dimension Column | AdventureWorks_Level01.dbo.SalesOrderHeader.OrderDate | datetime | int | Lookup Date Key | Keep | Need it to provide individual Sales orders
DWAdventureWorks_Level01.dbo.FactSalesOrders.CustomerKey (FK) | Dimension Column (FK) | AdventureWorks_Level01.dbo.SalesOrderHeader.CustomerID | int | int | Lookup Customer Key | Keep | Nice to have, so that links can be made to source data easily
| Dimension Column (FK) | AdventureWorks_Level01.dbo.SalesOrderHeader.CreditCardID | int | NA |  | Don’t Keep | Not needed since sales by a given credit card id is not likely to be useful
| Dimension Column | AdventureWorks_Level01.dbo.SalesOrderHeader.CreditCardApprovalCode | varchar | NA |  | Don’t Keep | Not needed since sales by a given credit card approval code is not likely to be useful
| Dimension Column | AdventureWorks_Level01.dbo.SalesOrderHeader.TotalDue | money | NA |  | Don’t Keep | Not needed since this represents aggragate data at a higher grain then our measures
| Dimension Column | AdventureWorks_Level01.dbo.SalesOrderHeader.Comment | nvarchar | NA |  | Don’t Keep | Not needed since there is no data in this column
DWAdventureWorks_Level01.dbo.FactSalesOrders (Part of fact table) | Fact Table Data | AdventureWorks_Level01.dbo.SalesOrderDetail | Table | Table |  | Keep | Need it to provide individual Sales orders
DWAdventureWorks_Level01.dbo.FactSalesOrders.SalesOrderID (redundent) | Dimension Key Column | AdventureWorks_Level01.dbo.SalesOrderDetail.SalesOrderID | int | int |  | Keep | Must have it to link to other tables and is the Key Identifier
DWAdventureWorks_Level01.dbo.FactSalesOrders.SalesOrderDetailID | Dimension Key Column | AdventureWorks_Level01.dbo.SalesOrderDetail.SalesOrderDetailID | int | int |  | Keep | Nice to have to define the granularity of the measures and is a Key Identifier
DWAdventureWorks_Level01.dbo.FactSalesOrders.ProductKey (FK) | Dimension Column (FK) | AdventureWorks_Level01.dbo.SalesOrderDetail.ProductID | int | int | Lookup Product Key | Keep | Nice to have, so that links can be made to source data easily
DWAdventureWorks_Level01.dbo.FactSalesOrders.OrderQty | Measure Column | AdventureWorks_Level01.dbo.SalesOrderDetail.OrderQty | smallint | int | Cast to int | Keep | Must have since it is our measure
DWAdventureWorks_Level01.dbo.FactSalesOrders.ActualUnitPrice | Measure Column | AdventureWorks_Level01.dbo.SalesOrderDetail.UnitPrice | money | decimal (18,4) | Cast to Decimal(18,4) | Keep | Must have since it is our measure
| Measure Column | AdventureWorks_Level01.dbo.SalesOrderDetail.UnitPriceDiscount | money | NA |  | Don’t Keep | Not needed since this data does not appear to be complete (Suspect)
DWAdventureWorks_Level01.dbo.DimDates | Dimension Table Data | NA | NA | Table |  | Added | Added for Date Support
DWAdventureWorks_Level01.dbo.DimDates.DateKey | Dimension Surrogate Key | NA | NA | int | Generate with SQL Script | Added | Added for Date Support
DWAdventureWorks_Level01.dbo.DimDates.FullDate | Dimension Key Column | NA | NA | datetime | Generate with SQL Script | Added | Added for Date Support
DWAdventureWorks_Level01.dbo.DimDates.FullDateName | Dimension Column | NA | NA | nvarchar (50) | Generate with SQL Script | Added | Added for Date Support
DWAdventureWorks_Level01.dbo.DimDates.MonthID | Dimension Column | NA | NA | int | Generate with SQL Script | Added | Added for Date Support
DWAdventureWorks_Level01.dbo.DimDates.MonthName | Dimension Column | NA | NA | nvarchar (50) | Generate with SQL Script | Added | Added for Date Support
DWAdventureWorks_Level01.dbo.DimDates.YearID | Dimension Column | NA | NA | int | Generate with SQL Script | Added | Added for Date Support
DWAdventureWorks_Level01.dbo.DimDates.YearName | Dimension Column | NA | NA | nvarchar (50) | Generate with SQL Script | Added | Added for Date Support
Object Name | Description | Source | Source Type | Destination Type

## ETL Objects
SSIS ETL Objects Worksheet
Object Name | Type | Description | Connection
DWAdventureWorksETL | SSIS Package | The name of the SSIS Package | NA
AdventureWorks_Level01 | OLEDB Connection | Provides a connection to the original source database | NA
DWAdventureWorks_Level01 | OLEDB Connection | Provides a connection to the new destination database | NA
Pre Load Tasks | Sequence Container | Used to group the pre load tasks | NA
Drop FKs Execute SQL Task | Execute SQL Task | Runs SQL code to drop the DW foreign key constraints | DWAdventureWorks_Level01
Clear Tables Execute SQL Task | Execute SQL Task | Runs SQL code to truncate the data from the DW tables | DWAdventureWorks_Level01
Load Dimension Tables | Sequence Container | Used to group the dimension table loading tasks | NA
Fill DimCustomers Data Flow | Data Flow Task | Uses a SSIS OLEDB Source and Destination to fill DimCustomer | NA
Customers OLEDB Source | OLEDB Source | Runs SQL code to get Source data from Customers | AdventureWorks_Level01
DimCustomers OLEDB Destination | OLEDB Destination | Perform a Bulk insert into the DimCustomers table | DWAdventureWorks_Level01
Fill DimProducts Data Flow | Data Flow Task | Uses a SSIS OLEDB Source and Destination to fill DimProducts | NA
Products OLEDB Source | OLEDB Source | Runs SQL code to get Source data from Products, ProductSubCategory, and ProductCategory | AdventureWorks_Level01
DimProducts OLEDB Destination | OLEDB Destination | Perform a Bulk insert into the DimProducts table | DWAdventureWorks_Level01
Fill DimDates Execute SQL Task | Execute SQL Task | Runs SQL code to Fill the DimDates table with data | DWAdventureWorks_Level01
Load Fact Tables | Sequence Container | Used to group the fact table loading tasks | NA
Fill FactSalesOrders Data Flow | Data Flow Task | Uses a SSIS OLEDB Source and Destination to fill FactSalesOrders | NA
SalesOrder Header and Details OLEDB Source | OLEDB Source | Runs SQL code to get Source data from SalesOrderHeader and SalesOrderDetails, plus lookup Dim keys | DWAdventureWorks_Level01
FactSalesOrders OLEDB Destination | OLEDB Destination | Perform a Bulk insert into the FactSalesOrders table | DWAdventureWorks_Level01
Post Load Tasks | Sequence Container | Used to group the post load tasks | NA
Replace FKs Execute SQL Task | Execute SQL Task | Runs SQL code to add the DW foreign key constraints | DWAdventureWorks_Level01

## Cubes and Dimensions
SSAS Objects Worksheet
Object Name | Description